## Sheet1
Iteration Number:
|  | Expected Total effort: |  |  |  | 206
Days In Sprint:
Burndown Chart
User Stories |  | Days (Points Completed) | [5 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | Task Balance | Percentage Completed
Users will be able to see and read current events, stories and top resources from the MIT home page. | 37 | 2 | 7 | 6 | 8 | 7 | 7 | 0 | 100%
Users will be able to get contact info from contact page. Users will be able to deal with enquiries from feedback page. | 37 | 3 | 3 | 7 | 10 | 10 | 4 | 0 | 100%
Users will be able to read admission information, guidelines and can get aid from MIT admission page. | 35 | 4 | 10 | 8 | 6 | 5 | 2 | 0 | 100%
Users will be able to know about MIT services such as research centers, labs, programs and more from their research page. Users will be able to read world wide latest news from the news page. | 46 | 6 | 11 | 10 | 7 | 4 | 6 | 2 | 95.65%
User will be able to read about the MIT mission, community, faculty and leadership from About page. | 28 | 2 | 7 | 4 | 6 | 6 | 3 | 0 | 100%
Users will be able to read success stories from alumni news page. So users can access things from the past post. | 23 | 2 | 8 | 8 | 1 | 4 | 1 | -1 | 104.3%
Effort Remaining | 206 | 187 | 141 | 98 | 60 | 24 | 1 | 1 | 99.51%
Ideal Trend | 206 | 195.7 | 185.4 | 175.1 | 164.8 | 154.5 | 144.2
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days